## Slide 1: DEVELOPMENT OF INTEGRATED WEARABLE DEVICE FOR REMOTE MONITORING OF PREGNANT WOMEN IN GHANA
UNIVERSITY OF GHANA
Group Members
Owoh Einsteina Ofunne - 10943874
Anane George Nyarko – 10947340
Adika Nathaniel - 10957036
DATE: 28th March,2025
Project Supervisor
Dr. Godfrey Mills
Co-Supervisor
Prof. Elsie Effah Kaufmann

## Slide 2: COLLABORATORS
Nathaniel Sakyi Adibuer, IT Consortium
Dr. Frank Amegah, Korle-Bu Teaching Hospital

## Slide 3: PROJECT ACTIVITIES
Research and Data Gathering
Thesis Documentation
Hardware and Software System Design
Visit to Antenatal Clinic
Procurement of Components
Mobile App development
Wearable Device development

## Slide 4: PROJECT ACTIVITIES
Exploration of AI models
AI Model Development

## Slide 5: PROJECT TIMELINES
Research and Data Gathering - December 23rd to January 8th
Thesis Documentation - December 23rd to January 8th
Hardware and Software System Design - December 23rd to January 8th
Visit to Antenatal Clinic - January 12th
Procurement of Components - January 16th to January 18th
AI model development - January 20th to February 25th
Mobile App development - February 10th to March 15th
Wearable Device development - March 15th to May 16th

## Slide 6: PROJECT TIMELINES
System Integration - May 17th - June 13th
Testing In Antenatal clinic - June 15th - August 3rd

## Slide 7: TASK DELEGATION
Owoh Einsteina Ofunne - AI Model Development
George Anane Nyarko - Mobile App Development
Adika Nathaniel - Wearable Device Development

## Slide 8: PROGRESS
Completion of mobile application to 90%
Complete training of models for gestational diabetes, anemia and preeclampsia
System Requirements, Specifications, System Diagram of the Hardware System

## Slide 9: NEXT LINE OF ACTION
Online meet with medical officer to clarify some questions
Proteus Simulation of Hardware System

## Slide 10: MISCELLANEOUS
QUESTIONS/FEEDBACK